## March4-10
Date | Time start | Time end | Total time spent | Description | Total time for day | Total time for week | Burn down chart
Week 1 |  | Sept. 12th - Sept. 19 |  |  |  | 5:03
2024-09-12 |  |  |  |  | 4:30
Abdul | 13:00 | 14:30 | 1:30 | Setup Gitlab Repo |  |  |  | Burned down |  | Balance |  | Daily Completed
Gavin | 13:00 | 14:30 | 1:30 | Setup Gitlab Repo |  |  | Day | Planned | Actual | Planned | Actual
Leo | 13:00 | 14:30 | 1:30 | Setup Gitlab Repo |  |  | 0 |  |  | 94:30 | 94:30 | #N/A
2024-09-18 |  |  |  |  | 0:33 |  | 1 | 4:30 | 1:42 | 90:00 | 92:48 | 1:42
Kip | 21:28 | 22:01 | 0:33 | Setup Gitlab Repo |  |  | 2 | 4:30 | 1:15 | 85:30 | 91:33 | 1:15
Week 2 |  | Oct.21st - Oct.27th |  |  |  | 1:42 | 3 | 4:30 | 2:16 | 81:00 | 89:17 | 2:16
2024-10-21 |  |  |  |  | 1:42 |  | 4 | 4:30 | 10:30 | 76:30 | 78:47 | 10:30
Gavin | 14:30 | 15:30 | 1:00 | Brainstorm Ideas for the game |  |  | 5 | 4:30 | 0:37 | 72:00 | 78:10 | 0:37
Leo | 13:30 | 14:12 | 0:42 | Research on Gitlab commands |  |  | 6 | 4:30 | 1:00 | 67:30 | 77:11 | 1:00
|  |  | 0:00 |  |  |  | 7 | 4:30 | 3:32 | 63:00 | 73:38 | 3:32
|  |  | 0:00 |  |  |  | 8 | 4:30 | 4:22 | 58:30 | 69:16 | 4:22
|  |  | 0:00 |  |  |  | 9 | 4:30 | 3:32 | 54:00 | 65:44 | 3:32
|  |  | 0:00 |  |  |  | 10 | 4:30 | 1:51 | 49:30 | 63:53 | 1:51
|  |  | 0:00 |  |  |  | 11 | 4:30 | 1:35 | 45:00 | 62:18 | 1:35
|  |  | 0:00 |  |  |  | 12 | 4:30 | 10:30 | 40:30 | 51:48 | 10:30
|  |  | 0:00 |  |  |  | 13 | 4:30 | 5:25 | 36:00 | 46:23 | 5:25
|  |  | 0:00 |  |  |  | 14 | 4:30 | 5:23 | 31:30 | 41:00 | 5:23
2024-10-22 |  |  |  |  | 1:15 |  | 15 | 4:30 | 5:25 | 27:00 | 35:36 | 5:25
Gavin | 9:00 | 10:15 | 1:15 | Practicing Godot |  |  | 16 | 4:30 | 5:44 | 22:30 | 29:52 | 5:44
|  |  | 0:00 |  |  |  | 17 | 4:30 | 2:19 | 18:00 | 27:33 | 2:19 | Burned Down Planned: The number of hours (pts) you plan to do each day
|  |  | 0:00 |  |  |  | 18 | 4:30 | 3:30 | 13:30 | 24:04 | 3:30 | Burn Down Actual: The actual number of hours (pts) achieved that day
|  |  | 0:00 |  |  |  | 19 | 4:30 | 3:48 | 9:00 | 20:16 | 3:48 | Balance Planned: The number of planned hours (pts) remaining
|  |  | 0:00 |  |  |  | 20 | 4:30 | 20:16 | 4:30 | 0:00 | 20:16 | Balance Actual: An estimate of the actual number of hours (pts) remaining
|  |  | 0:00 |  |  |  | 21 | 4:30 | 0:00 | 0:00 | 0:00 | 0:00 | Daily Completed: Actual number of hours completed
0:00
0:00
0:00
0:00
2024-10-23 |  |  |  |  | 2:16
Leo | 17:00 | 18:16 | 1:16 | Making Tutorial of Gitlab Commands
Abdul | 17:30 | 18:30 | 1:00 | Searching tutorials for Godot game design
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
2024-10-24 |  |  |  |  | 10:30
Gavin | 13:30 | 17:00 | 3:30 | GroupMeeting, Gather Ideas, Design Level
Leo | 13:30 | 17:00 | 3:30 | GroupMeeting, Gather Ideas, Design Level
Abdul | 13:30 | 17:00 | 3:30 | GroupMeeting, Gather Ideas, Design Level
0:00
0:00
0:00
0:00
0:00
0:00
2024-10-25 |  |  |  |  | 0:37
Gavin | 8:55 | 9:32 | 0:37 | Suggesting ideas for the game
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
2024-10-26 |  |  |  |  | 1:00
Gavin | 12:01 | 13:00 | 1:00 | Planning on the mechanics of the game
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
2024-10-27 |  |  |  |  | 3:32
Gavin | 12:01 | 13:00 | 1:00 | Helped implement some features
Abdul | 13:23 | 15:55 | 2:33 | Implement Tilemap, and draw partial background
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
Week 3 |  | Oct.28th - Nov.3rd |  |  |  | 34:49
2024-10-28 |  |  |  |  | 4:22
Leo | 8:00 | 10:00 | 2:00 | Made temp idle character
Abdul | 13:20 | 15:42 | 2:22 | Finished background, added collide layer
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
2024-10-29 |  |  |  |  | 1:51
Gavin | 12:08 | 13:59 | 1:51 | Downloading Assets to be used
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
2024-10-30 |  |  |  |  | 1:35
Gavin | 9:08 | 10:44 | 1:35 | Researching more about Godot
2024-10-31 |  |  |  |  | 10:30
Gavin | 13:30 | 17:00 | 3:30 | GroupMeeting, Collision learning, Gitlab Debug
Leo | 13:30 | 17:00 | 3:30 | GroupMeeting, Collision learning, Gitlab Debug
Abdul | 13:30 | 17:00 | 3:30 | GroupMeeting, Collision learning, Gitlab Debug
2024-11-01 |  |  |  |  | 5:25
Leo | 12:08 | 17:33 | 5:25 | Made Smoother Idle and partial Walk Animation
2024-11-02 |  |  |  |  | 5:23
Gavin | 16:08 | 18:30 | 2:22 | Learning how to add label nodes
Abdul | 17:02 | 20:03 | 3:01 | Finished painting collide area. Finished Level 1 making.
2024-11-03 |  |  |  |  | 5:44
Leo | 10:08 | 15:52 | 5:44 | Finished Move, Jump Animation PhotoEditing
Week 4 |  | Nov.4th - Nov.10th |  |  |  | 29:52
2024-11-04 |  |  |  |  | 2:19
Gavin | 21:12 | 23:30 | 2:19 | Suggesting features to implement
2024-11-05 |  |  |  |  | 3:30
Gavin | 13:31 | 17:00 | 3:30 | Helping fix the gitlab errors for the group
2024-11-06 |  |  |  |  | 3:48
Gavin | 19:08 | 21:59 | 2:51 | Implementing the character flip animation
Leo | 18:08 | 19:06 | 0:57 | Died Animation Attempted, will fix later
2024-11-07 |  |  |  |  | 20:16
Gavin | 13:30 | 17:00 | 3:30 | GroupMeeting Debug Gitlab
Gavin | 17:22 | 24:00 | 6:38 | Recording the demo of the prototype
Leo | 13:30 | 17:00 | 3:30 | GroupMeeting Debug Gitlab
Leo | 17:22 | 24:00 | 6:38 | Paperwork, logs
Abdul | 13:30 | 17:00 | 3:30 | GroupMeeting Debug Gitlab, minor fixes
2024-11-08 |  |  |  |  | 0:00
2024-11-09 |  |  |  |  | 0:00
2024-11-10 |  |  |  |  | 0:00
Week 5 | [5 empty] | 381:31
2024-11-11 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-12 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-13 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-14 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-15 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-16 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-17 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-18 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-19 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-20 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-21 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-22 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-23 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-24 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-25 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-26 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-27 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-28 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-29 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-11-30 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-12-01 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-12-02 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-12-03 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-12-04 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-12-05 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-12-06 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-12-07 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-12-08 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-12-09 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51
2024-12-10 |  |  |  |  | 47:41
| 0:08 | 23:59 | 23:51
| 0:08 | 23:59 | 23:51